## Sheet1
PREVENTION PROGRAM PLAN
Name of Program |  |  |  |  | Guiding Good Choices
Description of Prevention Program Activites |  |  |  | Prevention parenting program was formerly known as Preparing for the Drug Free Years. It is a parent skill building group program to help parents learn skills and practice influencing their children in preventing drug use and other risky behaviors.
PARTICIPANT LEVEL OUTCOMES
Participant Level Outcomes |  | When will you conduct the measures |  | What is the measure of change? |  |  | What measurement tool to measure the change |  | Who responsible for participant outcomes?
Change in parents knowledge |  | Pre test at first session and post after completion of 5 parenting sessions |  | 75% of parents who participate in prevention program will report increased awareness of extent of substance use in young people |  |  | Program pre/post knowledge questionnaires and a satisfaction survey |  | GGC Coordinator & Facilitators
Change in parents attitudes |  | Pre test at first session and post after completion of 5 parenting sessions |  | 70% of parents who participate in prevention program will report confidence in the ability of parents to influence their children to engage in healthy behaviors |  |  | Program pre/post knowledge questionnaires and a satisfaction survey |  | GGC Coordinator & Facilitators
Increase in parents skills |  | Pre test at first session and post after completion of 5 parenting sessions |  | 65% of parents will report increased opportunities to teach child conflict management strategies |  |  | Program pre/post knowledge questionnaires and a satisfaction survey |  | GGC Coordinator & Facilitators
Change in family’s behavior |  | Pre test at first session and post after completion of 5 parenting sessions |  | 80% of parents who participate in prevention program will report an increase in family bonding activities |  |  | Program pre/post knowledge questionnaires and a satisfaction survey |  | GGC Coordinator & Facilitators
TARGET POPULATION (To receive the prevention services)
Youth Population to Receive Services |  |  |  | Adult Population to Receive Services |  |  | Community Population to Receive Services
Proposed Number | % of total | By Grade | School | Proposed Number | % of total | Relationship to youth | Proposed Number | % of total | Relationship to Adult/Youth
|  | 5th & 6th | Anytown School ID | 116 | 25% | Families of Children
Recruitment Strategies | [5 empty] | Incentives
o Schools (Open house in fall at 6 elementary schools in Anytown School District, through teachers, other school professionals, room mothers, and by using phone-tree for recruitment; Parent groups/PTA/School Board) o Encourage prominent citizens to pilot and share with other parents o For Hispanic families, through migrant education and XYZ parent meetings o Community (churches, Kiwanis and Lions Club) o Media (newspaper, local radio/TV, community bulletin boards, newsletter opportunities o Youth recreation through school and sporting events o Community professionals o Businesses (poster in windows) o Physicians (refer youth as they transition to middle school) o Recruit 8-10 community volunteers, including at least one bilingual to encourage other families to attend | [5 empty] | o Child care offered at all parent training sessions o Pizza or other light meals o Refreshments for meetings not at mealtime o Family activity passes
Which Agencies & Organizations Will Deliver The Prevention Services (proposed) |  | Where Prevention Service will be Delivered |  | Dosage Each Program |  |  | When Will Services Be Provided? |  | Program Service Cycles (proposed)
|  |  |  | # Cycles time period | # Sessions each cycle | Length in hrs each session
XYZ, a non-profit in Anytown, will implement Guiding Good Choices |  | Elementary schools Community locations such as library, churches, youth centers, local spots |  | 12-15 parent group cycles | 5 sessions 1/week for 5 weeks | 2 hours | September 2014 to June 2015 |  | Sept-Nov: 6 cycles Jan-Mar: 6 cycles Summer ̶ 1-3 cycles as possible
PROGRAM IMPLEMENTATION GOALS SUMMARY
Implementation Goals |  |  | Wo will Provide the Prevention Services? |  | Does this program need a coordinator? |  | How will Services be Provided? |  | Who Will Ensure Implementation Goals are Met?
Provide the prevention program: The Families That Care – Guiding Good Choices parenting program, 10 parents/group, consisting of 5 sessions at school and community sites to at least 25% (116) of 464 parents of Anytown 5-6th grade students |  |  | Team of 6 trained workshop facilitators – 2 per workshop Spanish contract interpreter as needed |  | Propose .33FTE parent workshop coordinator |  | Five-week period, two- hour parent training sessions based on the program manual |  | GGC Coordinator 6 GGCFacilitators

## Sheet2
Who will Deliver the Prevention Services | Where will Prevention Service be Delivered | What Agency will Coordinate Service Delivery | Dosage Each Program Service |  |  | Program Service Cycle
|  |  | # Cycles | # Sessions each cycle | Length in hrs each session | Begin Dates (proposed)
time period
Participant Level Outcomes
Participant Level Outcomes | When will you conduct the measures? | What is the measure of change? |  | What Measurement Tool to measure the change? |  | Who responsible for Participant Outcome?

## Sheet3
PROGRAM IMPLEMENTATION GOALS
Implementation Outcomes | Who will Provide the Prevention Services? | How will Services be Provided? | When Will Services Be Provided? | How Measure Implementation Outcomes? | Who Responsible Implementation Outcomes?
Provide the prevention program: The Families That Care – Guiding Good Choices parenting program, 10-13 parents in group, consisting of 5 sessions at school and community sites to at least 25% (116) of 464 parents of MRSD students in grades 4-5 | Team of one part-time staff and Russian and Spanish contract interpreter as needed. | Five-week period, two- hour parent training sessions based on the program manual. | September 2004 to June 2005 | Observation to check for implementation fidelity | GGC Coordinator
|  |  |  | Work sheet to confirm use of curriculum will be developed | 6 GGCFacilitators
Quarterly program progress